# COSC 251 — Sorting Algorithm Project

Group Presentation & Coding Project — Team Plan

Instructor: Visethboti Sin (v.sin@aupp.edu.kh)   |   Deadline: Sep 23, 11:59 PM   |   Algorithm choice due: Sep 14

# Team Role Split (5 Members)

Person 1 — Main Algorithm

- Codes the chosen sorting algorithm in Java (no built-in sort functions like Arrays.sort())

- Adds comments explaining how the algorithm works

- Explains this algorithm during the video presentation

Person 2 — Comparison Algorithms

- Codes Bubble Sort, Selection Sort, and Insertion Sort in Java

- Keeps the same method style/signature as Person 1's code so everything is easy to compare

Person 3 — Testing Setup

- Writes the main method / test driver that runs all 4 algorithms

- Adds counters for comparisons, swaps, and runtime

- Creates the 3 test datasets: 5, 1,000, and 1,000,000 elements

Person 4 — Results & Report

- Saves sorted output to .txt files

- Puts performance results (runtime, comparisons, swaps) into a clear table

- Writes the research report and the compile/run instructions (README)

Person 5 — Slides & Video

- Builds the presentation slides

- Records and edits the 20–30 minute video

- Submits the video to Canvas and shares it in the course Telegram group

# Suggested Order of Work

- Pick the algorithm and agree on shared Java method names as a group (by Sep 14)

- Person 1 & Person 2 code their algorithms at the same time

- Person 3 builds the testing/metrics setup once 1 & 2 have working code

- Person 4 writes the report and formats results once real output exists

- Person 5 builds slides/video and submits everything by Sep 23

Heads up: test the 1,000,000-element dataset early. Bubble, Selection, and Insertion Sort are all O(n²) and can be very slow at that size — better to find out now than two days before the deadline.

# Project File Structure

COSC251_SortingProject/

├── src/

│   ├── Main.java                  (Test driver — runs all 4 algorithms on all 3 dataset sizes)

│   ├── sorts/

│   │   ├── MainAlgorithm.java      (Your chosen algorithm, e.g. MergeSort.java)

│   │   ├── BubbleSort.java

│   │   ├── SelectionSort.java

│   │   └── InsertionSort.java

│   ├── utils/

│   │   ├── DatasetGenerator.java   (Generates the 5 / 1,000 / 1,000,000 element arrays)

│   │   ├── SortMetrics.java        (Tracks comparisons, swaps, runtime)

│   │   └── FileWriter.java         (Saves sorted output + results to .txt)

│   └── SortAlgorithm.java          (Optional shared interface, e.g. sort(int[] arr))

├── output/

│   ├── sorted_small_5.txt

│   ├── sorted_medium_1000.txt

│   ├── sorted_large_1000000.txt

│   └── performance_results.txt

├── report/

│   └── Research_Report.pdf (or .docx)

├── slides/

│   └── Presentation.pptx

└── README.md                       (Compile/run instructions)

Tip: Use a shared interface (SortAlgorithm.java) so every algorithm has the same method signature — this lets Person 3 loop through all 4 algorithms with one clean piece of test code instead of writing separate calls for each.

# Submission Checklist

- Algorithm choice reported in Telegram group (by Sep 14, no duplicates across groups)

- Java implementation of the chosen algorithm (no built-in sort calls)

- Java implementations of Bubble, Selection, and Insertion Sort

- Test program / main method that runs and compares all 4 algorithms

- Test cases for 5, 1,000, and 1,000,000 element datasets

- Sorted output saved to .txt files

- Performance results captured: runtime, comparisons, swaps/movements

- Clear compile/run instructions (README)

- Written research report

- Presentation slides

- 20–30 minute video, submitted to Canvas AND shared in Telegram (by Sep 23, 11:59 PM)